Invoice Payment Automation

Effort & Cost Estimation

Prepared for: Dr. Stefan Kloss

CFO, BeyondBookings

Prepared by:  Fayssal El Mofatiche

CEO & Founder, Flowistic

Date: February 2025

Version: 1.0 (Draft)

CONFIDENTIAL

This document contains proprietary information prepared exclusively for BeyondBookings. Distribution without written consent from Flowistic is not permitted.

# Executive Summary

BeyondBookings currently processes approximately 1,000 supplier invoices per year through a dedicated Outlook mailbox. Each invoice is manually reviewed, data is extracted by hand, and payments are initiated via manual bank transfers. Additionally, the CFO maintains a local Access database to consolidate financial data, manually pulling customer information from HubSpot.

This proposal outlines an AI-powered automation solution that eliminates these manual workflows. The solution is structured as modular components that can be delivered incrementally, allowing BeyondBookings to realize value early while managing risk and investment.

### Proposed Components

Core: AI-powered invoice extraction and approval workflow (always included)

Variant A: Automated payment execution and operational hardening

Variant B: Cloud-based CFO financial consolidation replacing the Access database

Variant C: Client-facing invoice submission portal replacing the Outlook inbox

### Investment Overview

| Package | Scope | Effort | Cost |
| --- | --- | --- | --- |
| A: Core only | Core | 19-26 PD | €22,800 - €31,200 |
| B: Core + CFO | Core + Var. B | 47-64 PD | €49,350 - €67,200 |
| C: Core + Portal | Core + Var. C | 47-64 PD | €49,350 - €67,200 |
| D: Core + CFO + Portal | Core + Var. B + C | 75-102 PD | €71,250 - €96,900 |
| E: Everything | Core + Var. A + B + C | 93-126 PD | €81,840 - €110,880 |

We recommend Package D as the optimal engagement: it delivers Core automation plus both the CFO dashboard and client portal at a 20% reduced rate, while deferring payment automation (Variant A) until invoice extraction accuracy is validated.

# Understanding Your Needs

## Current Situation

~1,000 invoices/year received via a dedicated Outlook mailbox (up from 500 last year)

Mix of digitally generated and scanned PDF invoices

Manual data extraction, review, and payment initiation via bank transfer

Single approver workflow (lean team of 10-12 people)

CFO manually consolidates financials in a local Access database

Customer data is pulled manually from HubSpot into the Access database

## Current Technology Stack

| System | Purpose | Status |
| --- | --- | --- |
| Outlook | Invoice reception (dedicated mailbox) | To be automated / replaced |
| Lexoffice | Bookkeeping | Keep – integrate via API |
| HubSpot | CRM – customer & deal management | Keep – integrate via API |
| Access Database | CFO financial consolidation | To be replaced |
| Manual Bank Transfer | Payment execution | To be automated (Variant A) |

## Key Challenges

Time-consuming manual invoice processing prone to human error

No real-time visibility into invoice status for suppliers

Fragmented financial data across multiple disconnected systems

Local Access database creates single-point-of-failure risk and limits collaboration

Scaling to higher invoice volumes will compound manual effort

# Core: Invoice Processing MVP

The core of the solution: an AI agent that monitors the Outlook mailbox, extracts invoice data using OCR and language models, and presents it for approval in a dashboard. Approved invoices are pushed directly to Lexoffice.

## Detailed Breakdown

| Task | Description | PD | Hours |
| --- | --- | --- | --- |
| Email Ingestion | Microsoft Graph API integration to monitor the Outlook mailbox, extract PDF attachments, queue for processing | 2-3 | 16-24h |
| PDF Processing | Digital PDF text extraction + OCR for scanned documents (Azure Document Intelligence) | 3-4 | 24-32h |
| AI Data Extraction | LLM-based field extraction (vendor, invoice #, date, due date, amount, VAT, IBAN, line items) with confidence scoring | 4-5 | 32-40h |
| Approval Dashboard | Web UI: pending invoices list, side-by-side PDF viewer + extracted data, approve/reject/edit, email notifications | 3-4 | 24-32h |
| Lexoffice Integration | Push approved invoice data into Lexoffice via API | 2-3 | 16-24h |
| Infrastructure & Auth | Hosting, authentication, basic monitoring, environment setup | 2-3 | 16-24h |
| Testing & QA | End-to-end testing with real invoices, edge case handling, accuracy tuning | 3-4 | 24-32h |

Core Total: 19-26 PD (152-208 hours)

### Deliverables

Invoices automatically read from Outlook and parsed by AI

Extracted data presented for review in an approval dashboard

Approver can review, correct, and approve or reject each invoice

Approved invoices pushed to Lexoffice with all fields pre-filled

Payment still triggered manually (fully prepared in Lexoffice)

# Variant A: Full Payment Automation

Once invoice extraction accuracy is validated through Core, this variant adds automated payment execution and operational improvements based on real-world learnings.

## Detailed Breakdown

| Task | Description | PD | Hours |
| --- | --- | --- | --- |
| Payment Automation | Banking API integration (e.g. finAPI) or Lexoffice payment triggering for approved invoices | 5-6 | 40-48h |
| Duplicate Detection | Invoice deduplication, vendor matching against known database | 3-4 | 24-32h |
| Accuracy Feedback Loop | Use approver corrections to improve extraction accuracy over time | 3-4 | 24-32h |
| Notifications & Alerts | Reminders for pending approvals, payment confirmations, failure alerts | 2-3 | 16-24h |
| Reporting | Dashboard: processed/pending/rejected counts, monthly spend overview | 2-3 | 16-24h |
| Hardening | Error handling, retry logic, GDPR data handling review, audit logging | 3-4 | 24-32h |

Variant A Total: 18-24 PD (144-192 hours)

# Variant B: CFO Financial Consolidation

Replace the local Access database with a cloud-based financial consolidation layer. Automates data feeds from HubSpot and Lexoffice, and connects to the invoice automation pipeline from Core. Can be executed in parallel with Core.

## Discovery & Data Migration (1-2 weeks)

| Task | Description | PD | Hours |
| --- | --- | --- | --- |
| Access DB Analysis | Reverse-engineer the existing database: tables, relationships, queries, reports | 3-4 | 24-32h |
| Data Model Design | Design a clean, normalized data model for financial consolidation needs | 2-3 | 16-24h |
| Data Migration | Migrate historical data from Access. Validate completeness with the CFO | 2-3 | 16-24h |

## Automated Data Integrations (2-3 weeks)

| Task | Description | PD | Hours |
| --- | --- | --- | --- |
| HubSpot Integration | Automated sync of customer data, deals, and revenue via HubSpot API. Scheduled sync + webhooks | 4-5 | 32-40h |
| Lexoffice Integration | Pull bookkeeping data (expenses, revenue, tax) from Lexoffice API | 3-4 | 24-32h |
| Invoice Pipeline Link | Connect Core invoice automation pipeline so approved/paid invoices flow into CFO view | 2-3 | 16-24h |
| Data Reconciliation | Automated cross-checks between sources with discrepancy flagging | 3-4 | 24-32h |

## CFO Dashboard (2-3 weeks)

| Task | Description | PD | Hours |
| --- | --- | --- | --- |
| Financial Overview | Consolidated dashboard: revenue, expenses, cash flow, outstanding invoices, AP/AR | 4-5 | 32-40h |
| Customer Financial View | Per-customer P&L combining HubSpot deal data with invoice/payment history | 3-4 | 24-32h |
| Reporting & Export | Monthly/quarterly reports, CSV/PDF export for accountant or tax advisor | 2-3 | 16-24h |
| Filters & Drill-Down | Filter by period, customer, vendor, category. Drill down to transactions | 2-3 | 16-24h |
| Testing & Validation | Validate numbers against Access database, iterate based on CFO feedback | 3-4 | 24-32h |

Variant B Total: 28-38 PD (224-304 hours)

### Deliverables

Local Access database fully replaced by cloud-based solution

HubSpot customer/revenue data synced automatically

Lexoffice bookkeeping data integrated automatically

Invoice pipeline data flows in from Core automation

CFO dashboard with consolidated financial overview, per-customer views, and exportable reports

Discrepancy detection between data sources

# Variant C: Client Invoice Portal

Replace the Outlook mailbox with a branded client-facing portal where suppliers upload invoices directly, track processing status in real-time, and communicate with BeyondBookings. Improves client experience and data quality through structured submissions.

## Portal Core (3-4 weeks)

| Task | Description | PD | Hours |
| --- | --- | --- | --- |
| Client Authentication | Secure login with invitation-based onboarding. Role management for multiple users per supplier | 4-5 | 32-40h |
| Invoice Upload | Drag-and-drop interface. Single/bulk PDF upload. Optional structured fields to improve extraction | 4-5 | 32-40h |
| Status Tracking | Real-time status: Uploaded → Processing → Under Review → Approved → Paid. Timeline per invoice | 4-5 | 32-40h |
| Feedback & Communication | Per-invoice comment thread. Rejection reasons with resubmission workflow | 3-4 | 24-32h |
| Email Notifications | Automated notifications on status changes. Configurable preferences | 2-3 | 16-24h |

## Integration & Migration (1-2 weeks)

| Task | Description | PD | Hours |
| --- | --- | --- | --- |
| Pipeline Integration | Connect portal uploads to Core processing pipeline. Dual-mode during transition | 3-4 | 24-32h |
| Dashboard Updates | Extend approval dashboard with client feedback capabilities | 2-3 | 16-24h |
| Client Onboarding Flow | Admin interface to invite clients, manage accounts, monitor usage | 2-3 | 16-24h |

## Branding & Polish (1 week)

| Task | Description | PD | Hours |
| --- | --- | --- | --- |
| UI/UX Design | Branded interface aligned with BeyondBookings identity. Mobile-responsive | 3-4 | 24-32h |
| Multi-language | German and English support | 1-2 | 8-16h |
| Testing & QA | End-to-end testing, cross-browser, mobile testing | 3-4 | 24-32h |

Variant C Total: 28-38 PD (224-304 hours)

### Deliverables

Branded client portal with secure login for suppliers

Drag-and-drop invoice upload (single and bulk)

Real-time status tracking for every submitted invoice

Per-invoice feedback and communication thread

Automated email notifications on status changes

Dual-mode ingestion: portal + Outlook during transition period

Admin interface for client account management

# Investment

## Rate Structure

Rates are tiered based on total engagement volume, rewarding larger commitments with a reduced daily rate:

| Engagement Volume | Daily Rate | Hourly Rate |
| --- | --- | --- |
| Up to 40 PD | €1,200/day | €150/h |
| 41-80 PD | €1,050/day | €130/h |
| 81-120 PD | €950/day | €120/h |
| 120+ PD | €880/day | €110/h |

## Per-Component Effort

| Component | Effort (PD) | Hours |
| --- | --- | --- |
| Core (Invoice Processing MVP) | 19-26 PD | 152-208h |
| Variant A (Full Payment Automation) | 18-24 PD | 144-192h |
| Variant B (CFO Consolidation) | 28-38 PD | 224-304h |
| Variant C (Client Portal) | 28-38 PD | 224-304h |

## Packaging Options

| Package | Scope | Effort | Rate | Investment |
| --- | --- | --- | --- | --- |
| A: Core only | Core | 19-26 PD | €1,200/day | €22,800 - €31,200 |
| B: Core + CFO | Core + Var. B | 47-64 PD | €1,050/day | €49,350 - €67,200 |
| C: Core + Portal | Core + Var. C | 47-64 PD | €1,050/day | €49,350 - €67,200 |
| D: Core + CFO + Portal | Core + Var. B + C | 75-102 PD | €950/day | €71,250 - €96,900 |
| E: Everything | Core + Var. A + B + C | 93-126 PD | €880/day | €81,840 - €110,880 |

## Savings at Scale

| Package | Rate Reduction | Saving / PD | Total Saving |
| --- | --- | --- | --- |
| A | Baseline | - | - |
| B / C | -12.5% | €150/day | €7,050 - €9,600 |
| D | -20.8% | €250/day | €18,750 - €25,500 |
| E | -26.7% | €320/day | €29,760 - €40,320 |

## Ongoing Infrastructure Costs

Estimated monthly running costs once the solution is in production:

| Service | Estimated Monthly Cost |
| --- | --- |
| OCR Service (provider TBD) | €50-100 |
| LLM API (GPT-4o / Claude) | €30-80 |
| Cloud Hosting | €30-60 |
| Database (PostgreSQL) | €20-50 |
| Email API (Microsoft Graph) | Included in M365 |
| Lexoffice API | Included in subscription |
| Banking API (Variant A) | €50-150 |
| Portal Auth & Email (Variant C) | €0-45 |

Estimated total infrastructure: €200-550/month (all components)

# Risks & Considerations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| OCR accuracy on scanned invoices | High | Budget tuning time, confidence scoring flags uncertain extractions for manual review |
| Diverse invoice layouts | Medium | LLM-based extraction handles variety well; feedback loop improves accuracy over time |
| Banking API complexity | Medium | Start with Lexoffice-triggered payments before full bank API integration |
| GDPR / data handling | Medium | Flag for legal review; ensure minimal data retention |
| GoBD compliance | Low-Med | Client to verify with tax advisor; may need compliant archiving |
| Access DB data quality | Medium | Legacy data may be inconsistent; budget time for cleanup and CFO validation |
| HubSpot data model | Low-Med | Map custom properties to financial model in discovery session |
| CFO adoption | Medium | Involve CFO early in dashboard design; iterative feedback sessions |
| Client portal adoption | Medium | Clear UX advantage and status tracking incentivize suppliers to switch from email |

# Recommendation

We recommend Package D (Core + Variant B + Variant C) as the optimal engagement. This delivers Core automation plus the CFO dashboard and client portal at a 20% reduced rate, while deferring payment automation (Variant A) until the system is proven.

## Proposed Timeline

| Period | Core (MVP) | Variant B (CFO) | Variant C (Portal) |
| --- | --- | --- | --- |
| Weeks 1-4 | Core pipeline development | Access DB analysis + data model | UI/UX design (parallel) |
| Weeks 5-8 | Dashboard + integrations | HubSpot & Lexoffice integration | Portal core development |
| Weeks 9-10 | Testing & go-live | CFO dashboard + validation | Integration + testing |
| Weeks 11-12 | Support & tuning | Refinement | Client onboarding |

## Value Delivered

Invoice processor: Automated extraction and approval workflow, eliminating manual data entry

CFO: Real-time financial consolidation replacing manual Access work

Suppliers: Self-service portal with full transparency on invoice status

## Alternative: Start Smaller

If budget is a constraint, Package B (Core + Variant B) addresses the two most painful manual workflows at €49,350-€67,200. The client portal can follow as a separate engagement.

# Next Steps

Review this proposal and confirm preferred package

Schedule a discovery session to review the Access database and HubSpot data model

Provide sample invoices (5-10 representative PDFs) for extraction accuracy testing

Confirm Lexoffice API access and Microsoft 365 admin permissions

Align on timeline and kick-off date

Fayssal El Mofatiche

CEO & Founder, Flowistic

Dare to deliver.

flowistic.ai